## Sheet1
| Project Roadmap | Start Month | 2025-06-02
|  | Q1 |  |  | Q2
| Portfolio Website | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
WK1 | Design & development | SOW | Contract&Content, Color theme | Wireframes | Home Page
WK2 | Design & development | About Me Page | Projects Page |  | *Blogs/Insights | Contact Page *Contact form *Email Forwarding
WK3 | Functionality | Optimization for mobile/tablet |  | CV embedded viewer | *Social Media Integration | CMS setup
WK4 | Functionality |  | On-Page SEO/GEO *reviews |  |  | Google Analytics Integration
WK5 | Functionality | Hosting Setup |  | Domain Configuration |  | Documentation
WK6 | Support |  | Handover & Training on Content Updating |  | *Post launch Bug Fixes(Continuous)